## Open Tasks
Sr. No. | Category | Item Description | Reported by | Reported On | Expected date of closure | Status | Remarks
2 | Amendment | Amendment of NFA: , if value of the NFA remains the same, then SJ sir’s name to appear by default. | Pramod Paranjape | 25-09-2018, Clarified on 28th Nov 18 |  | Need more clarity on editable fields of Amend NFA
5 | Amendment | User should be able to reduce the amount of the pre-approved NFA (than previous amount) | Pramod Paranjape | 27-09-2018, Clarified on 28th Nov 18 |  | Need more clarity on editable fields of Amend NFA
6 | Amendment | During Amendment, the hightest ever value to be considered before triggering RSR Sir's email ID. Also the logic of NFA Release mentioned below will be applicable for amendments as well. | Pramod Paranjape | 27-09-2018, Clarified on 28th Nov 18 |  | Need more clarity on editable fields of Amend NFA
12 | a. if the user selects ‘NO’ in the checkbox of “Group CFO approval obtained…” Statement | Group CFO’s name to be added as the signing authority automatically | Pramod Paranjape & Himanshu | 17-12-2018,
and
b. he does not select the Group CFO’s name manually in the approving team list
13 | a. if the user selects ‘NO’ in the checkbox of “Group CFO approval obtained…” Statement | Group CFO’s name should NOT be added as the signing authority automatically | Pramod Paranjape & Himanshu | 2018-12-17
and
b. he SELECTS the Group CFO’s name manuallyin the approving team list
14 | a. if the user SELECTS ‘YES’ in the checkbox of “Group CFO approval obtained…” Statement | Group CFO’s name should NOT be added as the signing authority automatically. Even if the user selects his name by mistake – same shall be removed | Pramod Paranjape & Himanshu | 2018-12-17
and
b. he SELECTS the Group CFO’s name manually in the approving team list

## Closed Tasks
Sr. No. | Category | Item Description | Reported by | Reported On | Expected date of closure | Status | Remarks
1 | NFA Creation | Increase number of plants to 30. Modify table to accommodate increased no. of plants | Pramod Paranjape | 2018-09-20 | 2018-09-21 | Done
3 | NFA to FTP | The version should be only numeric where as the one in the file is in the format ‘V 0.0’. | Amar Waghmare | 2018-09-26 |  | Done
4 | NFA to FTP | The text shouldn’t contain any semi colon(;) as it shifts the data that is stored in SAP database tables (screen shot attached). To resolve this if any semi colon(;) is found in any input text fields at eNFA poratl the same should be replaced by comma(,). | Amar Waghmare | 2018-09-26 |  | Done
7 | NFA Release | a. While creating / amending a NFA, following sentence to appear on the screen: ‘Group CFO approval (Project related Capital and Revenue expenses including contract packages) available?’ b. Only two check box option to be there "Yes" and "No" i. If the option selected by the user is "Yes", 1. A mandatory tab to be included of uploading the approval copy 2. Auto selection of Group CFO in the approving list to be disabled ii. If the option selected by the user is "No", 1. then the Group CFO should be selected by default as per the shared approval matrix of Group CFO. | Pramod Paranjape | 2018-09-27 |  | Done
8 | NFA Creation | Activate the following Currencies in E NFA Portal. *USD (US Dollars) *SGD (Singapore Dollars) *GBP (Great Britain Pound) *AED (Arab Emirates Dirham) | Sai Siddharth Maddirala | 2018-09-27 |  | Done
9 | Access Control | Access: Please restrict following menu options only to 1) Pramod Paranjape & 2) Amar Waghmare a. Company Code Management b. Plant Management c. Document Type Management d. Purchasing group Management | Pramod Paranjape |  |  | Done
11 | NFA to SAP | In order to ensure correct shake-hand between eNFA and the SAP, we would like to restrict the data size from eNFA as per attached text file. Field size is given in bracket. A) For all ‘plant’ fields the field size remains the same, i.e. 4 characters. B) Also the conversion of semicolon (;)to comma (,) to continue as earlier. | Pramod Paranjape |  |  | Done
10 | View & print NFA | View all Details: The NFA creator should be able to view all details enter or selected by him before and after submission of the NFA. Similarly he should be able to save PDF with all changes. | Sai Siddharth Maddirala |  | 30th November 18 | Done